## Sheet1
S.no | Query raised date | Pending work | Responsibility | Target date | Actual completion date | Status | Action to be taken / Follow
Pending work in OP 10
1 | 2026-07-15 | OP10 planger mechanism | Robonetics | 2026-07-28 |  | Not completed
2 | 2026-07-15 | Op 10 air planger | Robonetics | 2026-07-28 | 2026-08-01 | Completed | Installed dual air planger in op10
3 | 2026-07-15 | OP10 input table | Robonetics | 2026-07-27 |  | Not completed
4 | 2026-07-27 | OP10 conveyar bur removal brash | Robonetics
5 | 2026-08-10 | OP10 conveyar L plate
6 | 2026-07-27 | OP10 part present sensor | Robonetics | 2026-08-08
7 |  | OP10 training | Robonetics
8 |  | software | Robonetics
Ultra sonic washing
1 |  | UW cobot gripper install | Robonetics
2 |  | UW gripper pnematic | Robonetics
3 |  | UW PLC program | Robonetics
4 |  | UW HMI program | Robonetics
5 |  | UW robot programing | Robonetics
6 | 2026-07-15 | UW bin | Robonetics | 2026-07-28 |  | Not completed
7 |  | UW conveyar power Up | Robonetics
8 | 2026-07-27 | UW L clamp
9 | 2026-07-27 | UW conveyar painting | Robonetics
10 |  | UW conveyar pnematic supply | Robonetics
11 |  | UW conveyar sensor mounting | Robonetics
12 | 2026-07-15 | Vision rejection BIN | Robonetics | 2026-07-31 |  | Not completed
13 |  | Vision Pick and place check | Robonetics
14 |  | Vision communication check | Robonetics
15 |  | Vision encloser | LGB gear maintenance
16 |  | Oil washing conveyar installation | Robonetics
17 | 2026-07-15 | Oil washing pusher | Robonetics | 2026-07-31 |  | Not completed
18 |  | Oil washing sensor mounting | Robonetics