## Summary Dashboard
LGB COBOT-MACHINE TENDING AUTOMATION
Installation & Commissioning Tracker
PROJECT INFORMATION |  |  |  |  | PROJECT STATUS AT A GLANCE
Customer (End User) | DIAMLER |  |  |  | Overall Planned Duration (Days) |  | 24
Vendor / System Integrator | Multivista Global Pvt Ltd |  |  |  | Days Elapsed Since Install Start |  | 5
Project | Cobot-Based Sprocket Pick & Place Automation |  |  |  | Overall % Complete (weighted) |  | 15%
Site Location | P.Palayam, Coimbatore |  |  |  | Schedule Slippage (Days) |  | 0
Material Received at Site (Planned) | 2026-08-27 |  |  |  | Tasks Closed / Total |  | 3 / 20
Installation Start Date | 2026-09-02 |  |  |  | Open Punch List Items |  | 0
Planned SAT & Handover Date | 2026-08-30
Report / Update Date | 2026-09-07
PHASE-WISE PROGRESS SUMMARY (auto-computed from 'Installation Gantt')
Phase | Planned Start | Planned End | Planned Duration (d) | Tasks Closed/Total | Avg % Complete | Phase Status | RAG
Material Receipt & Inspection | 2026-08-27 | 2026-08-27 | 1 | 2 / 2 | 100% | Completed | GREEN
Mechanical & Robot Installation | 2026-09-02 | 2026-09-07 | 6 | 1 / 6 | 100% | In Progress | AMBER
Electrical & Panel Works | 2026-09-08 | 2026-09-09 | 2 | 0 / 2 | 0% | In Progress | AMBER
Automation, Programming & Calibration | 2026-09-10 | 2026-09-13 | 4 | 0 / 4 | 0% | Not Started | AMBER
Trials & Validation | 2026-09-14 | 2026-09-17 | 4 | 0 / 4 | 0% | Not Started | AMBER
Training & Handover | 2026-09-18 | 2026-09-19 | 2 | 0 / 2 | 0% | Not Started | AMBER
Notes: GREEN = phase fully closed. AMBER = in progress, on track. RED = at least one open task past its planned end date (overdue). Update 'Actual Start/End', '% Complete' and 'Status' in the Installation Gantt sheet daily; this dashboard recalculates automatically.
Formulas:
Planned Start = MINIFS('Installation Gantt'!$G5:G24,'Installation Gantt'!$C5:C24,[Phase])
Planned End = MAXIFS('Installation Gantt'!$H5:H24,'Installation Gantt'!$C5:C24,[Phase])
RAG = IF([Phase Status]="Completed","GREEN",IF(AND([Planned End]<TODAY(),[Phase Status]<>"Completed"),"RED","AMBER"))

## Installation Gantt
INSTALLATION & COMMISSIONING SCHEDULE – GANTT CHART (Material Receipt to SAT & Handover)
Site: P.Palayam. Coimbatore ¦ Vendor: RNT Automation ¦ Last Updated: (see Report Date on Dashboard)
S.No | Task ID | Phase | Activity | Responsibility | Pred. | Planned Start | Planned End | Plan Dur(d) | Actual Start | Actual End | Act Dur(d) | % Complete | Status | Delay (Days) | Remarks | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10
1 | I1 | Material Receipt & Inspection | Material Receipt at Customer Site | MULTIVISTA | - | 2026-08-27 | 2026-08-27 | 1 | 2026-08-27 | 2026-08-27 | 1 | 100% | Closed | 0 | Verify delivered materials
2 | I2 | Material Receipt & Inspection | Unloading & Inspection | MULTIVISTA + LGB | I1 | 2026-08-27 | 2026-08-27 | 1 | 2026-08-27 | 2026-08-27 | 1 | 100% | Closed | 0 | Check for transit damage
3 | I3 | Mechanical & Robot Installation | Machine Positioning & Alignment | MULTIVISTA | I2 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-02 | 2026-09-02 | 1 | 100% | Closed | 0 | As per approved layout
4 | I4 | Mechanical & Robot Installation | Conveyor and Lifter Installation & Leveling | MULTIVISTA | I3 | 2026-09-03 | 2026-09-03 | 1 |  |  |  |  | In Progress | 4 | Alignment and leveling
5 | I5 | Mechanical & Robot Installation | Cobot Pedestal Installation | MULTIVISTA | I3 | 2026-09-04 | 2026-09-04 | 1 |  |  |  |  | In Progress | 3 | Anchor and level
6 | I6 | Mechanical & Robot Installation | Cobot Installation | MULTIVISTA | I5 | 2026-09-05 | 2026-09-05 | 1 |  |  |  |  | In Progress | 2 | Robot mounting
7 | I7 | Mechanical & Robot Installation | Gripper Installation | MULTIVISTA | I6 | 2026-09-06 | 2026-09-06 | 1 |  |  |  |  | In Progress | 1 | Mechanical & pneumatic connections
8 | I8 | Mechanical & Robot Installation | Pneumatic Line Installation | MULTIVISTA | I4 | 2026-09-07 | 2026-09-07 | 1 |  |  |  |  | In Progress | 0 | FRL, tubing, valves
9 | I9 | Electrical & Panel Works | Control Panel Installation | MULTIVISTA | I2 | 2026-09-08 | 2026-09-08 | 1 |  |  |  |  | In Progress | 0 | Panel mounting
10 | I10 | Electrical & Panel Works | Electrical Wiring & Cable Dressing | MULTIVISTA | I9 | 2026-09-09 | 2026-09-09 | 1 |  |  |  | 0% | Not Started | 0 | Power and I/O wiring
11 | I11 | Automation, Programming & Calibration | PLC, HMI & Network Connections | MULTIVISTA | I10 | 2026-09-10 | 2026-09-10 | 1 |  |  |  | 0% | Not Started | 0 | Communication setup
12 | I12 | Automation, Programming & Calibration | Power ON & I/O Verification | MULTIVISTA | I11 | 2026-09-11 | 2026-09-11 | 1 |  |  |  | 0% | Not Started | 0 | Sensor and actuator checks
13 | I13 | Automation, Programming & Calibration | Robot Calibration | MULTIVISTA | I7,I12 | 2026-09-12 | 2026-09-12 | 1 |  |  |  | 0% | Not Started | 0 | TCP and frame calibration
14 | I14 | Automation, Programming & Calibration | PLC & Robot Program | MULTIVISTA | I13 | 2026-09-13 | 2026-09-13 | 1 |  |  |  | 0% | Not Started | 0
15 | I15 | Trials & Validation | Dry Run Trial | MULTIVISTA | I14 | 2026-09-14 | 2026-09-14 | 1 |  |  |  | 0% | Not Started | 0 | Without production parts
16 | I16 | Trials & Validation | Production Trial | Multivista + LGB | I15 | 2026-09-15 | 2026-09-15 | 1 |  |  |  | 0% | Not Started | 0 | Actual component validation
17 | I17 | Trials & Validation | Cycle Time Optimization | MULTIVISTA | I16 | 2026-09-16 | 2026-09-16 | 1 |  |  |  | 0% | Not Started | 0 | Performance tuning
18 | I18 | Trials & Validation | Safety Validation | MULTIVISTA + LGB | I17 | 2026-09-17 | 2026-09-17 | 1 |  |  |  | 0% | Not Started | 0 | Safety interlocks and E-stop testing
19 | I19 | Training & Handover | Operator & Maintenance Training | MULTIVISTA | I18 | 2026-09-18 | 2026-09-18 | 1 |  |  |  | 0% | Not Started | 0 | Customer training
20 | I20 | Training & Handover | Site Acceptance Test (SAT) & Handover | MULTIVISTA + LGB | I19 | 2026-09-19 | 2026-09-19 | 1 |  |  |  | 0% | Not Started | 0 | Final approval
Legend: |  |  | Planned Duration |  | Actual / Completed |  |  | Delayed / Overdue |  |  | Weekend |  |  | Today
Instructions for site team: fill in 'Actual Start', 'Actual End', '% Complete' and 'Status' daily as work progresses (blue text = editable). 'Delay (Days)' and the Gantt bars update automatically. Predecessor codes refer to Task ID (e.g. I3 = Task 3).

## Material Receiving Tracker
NECESSARY COMPONENTS FOR COMMISSIONING – MATERIAL RECEIVING TRACKER
Tracks every major equipment/component required at site for installation & commissioning, from vendor dispatch to receipt & inspection.
S.No | Component / Item | Specification / Model | Qty | Supplier / Vendor | Expected Dispatch Date | Expected Receipt at Site | Actual Receipt Date | Received Qty | Inspection Status | Remarks
1 | Cobot – Universal Robots UR12e | UR12e, 12.5 kg payload | 4 Nos | Universal Robots (OEM) | 2026-06-10 | 2026-06-22 |  |  | Pending
2 | Robot Gripper Set | PZN-plus 40-AS / PGN-plus-P 80-1-AS-SD | 4 Sets | Schunk (OEM) via MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
3 | Input Table System (OP10) | As per approved design | 1 No | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
4 | Belt Conveyor (OP10) | As per approved design | 1 No | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
5 | Roller Transfer Plate (UWM) | As per approved design | 1 No | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
6 | Lifting Roller Table (UWM) | As per approved design | 1 No | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
7 | Edge Belt Conveyor (UWM) | As per approved design | 1 No | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
8 | Powered Roller Conveyor with Oil Collecting Tray (OWM) | As per approved design | 1 No | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
9 | Cobot Pedestal Stand & Fabrication Items | As per approved design | 2 Sets + misc. | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
10 | PLC & HMI | Make/model as per BOQ | 1 Set | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
11 | Sensors & Control Panel Items | As per BOQ | 1 Lot | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
12 | Pneumatic Items (FRL, tubing, valves, cylinders) | As per BOQ | 1 Lot | MULTIVISTA | 2026-06-10 | 2026-06-22 |  |  | Pending
Note: item list and quantities are based on the vendor's procurement plan (bulk single-truck delivery). Update Specification/Model, Qty and Vendor fields as per the final approved BOQ / packing list, and confirm each line on physical receipt & inspection at site.

## Daily Progress Log
DAILY WORK PROGRESS TRACKING – VENDOR SITE ACTIVITY LOG
To be filled by site-in-charge every working day, cross-checking against the Installation Gantt schedule.
S.No | Date | Day | Activities Worked On (Task ID / Description) | Vendor Team Present | Man- power | Overall % Complete | Work Done Today / Progress Update | Issues / Delays Faced | Corrective Action | Reported By (Vendor) | Verified By (Customer)
1 | 2026-08-27 | Thu | Material Inward and Unload | -
2 | 2026-08-28 | Fri | - | -
3 | 2026-08-29 | Sat | - | -
4 | 2026-08-30 | Sun | - | -
5 | 2026-08-31 | Mon | - | -
6 | 2026-09-01 | Tue | - | -
7 | 2026-09-02 | Wed | Machine movement as per layout | Sudharsan, Marishiva |  | 100%
8 | 2026-09-03 | Thu
9 | 2026-09-04 | Fri
10 | 2026-09-05 | Sat
11 | 2026-09-06 | Sun
12 | 2026-09-07 | Mon
13 | 2026-09-08 | Tue
14 | 2026-09-09 | Wed
15 | 2026-09-10 | Thu
16 | 2026-09-11 | Fri
17 | 2026-09-12 | Sat
18 | 2026-09-13 | Sun
19 | 2026-09-14 | Mon
20 | 2026-09-15 | Tue
21 | 2026-09-16 | Wed
22 | 2026-09-17 | Thu
23 | 2026-09-18 | Fri
24 | 2026-09-19 | Sat
25 | 2026-09-20 | Sun
26 | 2026-09-21 | Mon
27 | 2026-09-22 | Tue
28 | 2026-09-23 | Wed
29 | 2026-09-24 | Thu
30 | 2026-09-25 | Fri
31 | 2026-09-26 | Sat
32 | 2026-09-27 | Sun
33 | 2026-09-28 | Mon
34 | 2026-09-29 | Tue
35 | 2026-09-30 | Wed
36 | 2026-10-01 | Thu
37 | 2026-10-02 | Fri
38 | 2026-10-03 | Sat
39 | 2026-10-04 | Sun
40 | 2026-10-05 | Mon
41 | 2026-10-06 | Tue
42 | 2026-10-07 | Wed
43 | 2026-10-08 | Thu
44 | 2026-10-09 | Fri
45 | 2026-10-10 | Sat
46 | 2026-10-11 | Sun
47 | 2026-10-12 | Mon
48 | 2026-10-13 | Tue
49 | 2026-10-14 | Wed
50 | 2026-10-15 | Thu
51 | 2026-10-16 | Fri
52 | 2026-10-17 | Sat
53 | 2026-10-18 | Sun
54 | 2026-10-19 | Mon
55 | 2026-10-20 | Tue
56 | 2026-10-21 | Wed
57 | 2026-10-22 | Thu
58 | 2026-10-23 | Fri
59 | 2026-10-24 | Sat
60 | 2026-10-25 | Sun
61 | 2026-10-26 | Mon
62 | 2026-10-27 | Tue
63 | 2026-10-28 | Wed
64 | 2026-10-29 | Thu
65 | 2026-10-30 | Fri
66 | 2026-10-31 | Sat
67 | 2026-11-01 | Sun
68 | 2026-11-02 | Mon
69 | 2026-11-03 | Tue
70 | 2026-11-04 | Wed
71 | 2026-11-05 | Thu
72 | 2026-11-06 | Fri
73 | 2026-11-07 | Sat
74 | 2026-11-08 | Sun
75 | 2026-11-09 | Mon
76 | 2026-11-10 | Tue
77 | 2026-11-11 | Wed
78 | 2026-11-12 | Thu
Note: rows are pre-dated from the planned installation-start date through today, so the delay period is also captured. Add further rows below (copy row formatting) as the project continues.

## Punch List
PUNCH LIST / OPEN ISSUES TRACKER
Snags, pending items and open issues raised during installation & commissioning, tracked to closure.
S.No | Date Raised | Area / Task | Issue Description | Raised By | Responsibility | Target Closure Date | Status | Actual Closure Date | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40