## Robotic project
S.no | Plant | Part Number | Customer | Requirement given by | Project Title | Project Description | Responsibility | Current status | Status | Start Date | EDC | Vendor
1 | P-palayam | 1018 | Stellantis | Tamilselvan | Stellantis line cobot automation | Using the UR cobot to automate the end to end process | Anand & Mynthan | OP10 installation completed and UW installation inprogress | Inprogress |  |  | Robonetics
2 | p-palayam | 931, 932 | Helical | Joythi | Helical line cobot automation | Using the UR cobot and one yawaka robot to automate the 8 cnc turning machine | Anand & Mynthan | Installation inprogress | Inprogress |  |  | Robonetics
3 | P-palayam | 1142 ,1217 | Daimler | Velmurugan | Daimler line cobot automation | Using the UR cobot to automate the 8 CNC turning machine | Anand & Mynthan | One cell installation inprogress | Inprogress |  |  | Multivista
4 | P-palayam | 1564B,1563 | Ather | Velmurugan | Ather line cobot automation | Using the ABB cobot automate the 10 CNC turning machine | Anand & Mynthan | I/p & o/p table are under manafacturing | Inprogress |  |  | Melss
5 | K-palayam | 841 | BMW | Neelamagam | RAD line cobot automation | Using UR and one amr for vmc machie to automate the 12 machien | Anand & Mynthan | I/p & o/p table are under manafacturing | Inprogress |  |  | Robonetics
6 | vallam |  | GPND | Manimaran | GPND line cobot automation | Using the UR cobot to automate the 8 CNC turning machine | Anand & Mynthan | waiting for part diagram in plant side | Inprogress |  |  | Robonetics , Melss
7 | Vallam |  |  | Manimaran | AMR | Using the AMR for material movement | Anand & Mynthan | Waiting for commercial | Inprogress |  |  | Robonetics , goat robotics ,
8 | Nagpur |  |  | Dhayalan | Presprocket line automation | Using the UR cobot to automate | Anand & Mynthan | Waiting for commercial | Inprogress |  |  | Firstdfeet,multivista
9 | Nagpur |  | Hotforging | Dhayalan | Hotforging | Using the robot to automate the hot forging machine | Anand & Mynthan | Waiting for Floor layout in plant side | Inprogress |  |  | Kuka
10 | Pongalur |  | Press | Sakthivel | Press unloading automation | Using the industrial robot | Anand & Mynthan | Waiting for input from plant side |  |  |  | Kuka
11 | Pongalur |  | Giging | Sakthivel | [7 empty] | Kuka
12 | Bawal | Rearsprocket | Deburing | Rajeshroshan | Deburing | Using Cobot to remove the bur in the rear sprocket | Anand & Mynthan | waiting for review and feedback from plant side |  |  |  | Multivista , robonetics

## Vision project
S.no | Plant | Part Number | Customer | Requirement given by | Project Title | Project Description | Responsibility | Current status | Status | Start Date | EDC | Vendor
1 | P.Palayam | 932 | Honda | Tamilselven | Timing Mark Identification | To Identify the Timing Mark in the Gear component | Anand | Demo completed,Plant side need to rise PR | Inprogress | 2026-03-03 | 2026-05-05
2 | P.Palayam | U666 | TVS | Balaganesh | Part identification | To identify the part present | Anand | PR reised | Inprogress | 27/05/2026
3 | P.Palayam | Gearbox | TVS | Balaganesh | Part identification | To identify the glue presence absence | Anand | POC need to complete | Inprogress | 27/05/2027
4 | p.palayam | Ather line | Ather | Sriram | Quailty Measurement | To measure the part ID ,OD ,Thickness and MOP | Anand | Discused with hikrobot | Inprogress | 17/04/2026
5 | p.palaym | 8T press | Ather | Naveen | OCR Identification | To capture the laser marking number in the shaft 1564B | Anand | Start planning for POC | Inprogress | 2026-11-09